## FA List
FY26 FA AD PROGRAM (listed by Designer as of 10/31/2025)
Project # | Description | District | Project Type | Project State | Ad Date | Ad Cost | Office Estimate | TFPC | Contract Cost | Project Manager | Designer
613921 | BOSTON- BRIDGE DECK PRESERVATION OF B-16-259 AND B-16-260 ON I-93 | District 6 | Bridge Preservation | Final Design | 11/01/2025 (adv). | 19801645 | 17354525 | 22234985.75 | 21537097.5 | Daragan,Alina
612050 | BRAINTREE- WEYMOUTH- RESURFACING AND RELATED WORK ON ROUTE 3 | District 6 | Limited Access Pavement Preservation | Final Design | 2025-12-27 |  | 9478027.7 | 11210946.86 | 11051582.97 | Nova,Eric
614009 | DEERFIELD TO NORTHAMPTON- INTERSTATE PAVEMENT PRESERVATION ON I-91 | District 2 | Limited Access Pavement Preservation | Final Design | 2025-12-27 |  | 10492776.5 | 12392483.58 | 12127617.15 | Nova,Eric
609399 | RANDOLPH- RESURFACING AND RELATED WORK ON ROUTE 28 | District 6 | Pavement Rehabilitation | 100% Design | 2025-12-27 |  | 5046656 | 6006174.4 | 5885571.6 | Lemrise,Koby
612064 | WESTPORT- DARTMOUTH- RESURFACING AND RELATED WORK ON I-195 | District 5 | Limited Access Pavement Preservation | Final Design | 2025-12-27 |  | 6862861.14 | 8051209.06 | 7934274.75 | Nova,Eric
613383 | LYNNFIELD- WAKEFIELD- INTERSTATE PAVEMENT PRESERVATION AND RELATED WORK ON I-95 | District 4 | Limited Access Pavement Preservation | Final Design | 2026-01-31 |  | 22933958.6 | 13422906.39 | 27096298.96 | Wilk,Daniel
609436 | HARWICH- BRIDGE PRESERVATION OF H-10-013, H-10-014 AND H-10-016 ALONG ROUTE 6 | District 5 | Bridge Preservation | Approved | 2026-04-04 |  | 2600000 | 3811800 | 3563600 | Napit,Albin
612061 | MATTAPOISETT- MARION- WAREHAM- RESURFACING AND RELATED WORK ON I-195 | District 5 | Limited Access Pavement Preservation | Approved | 2026-05-09 |  | 17800000 | 22969565 | 22339000 | Wilk,Daniel
613276 | READING- WILMINGTON- BRIDGE PRESERVATION, W-38-028 (2HR, 2HT) AND R-03-011 (2HK), I-93 (NB/SB) OVER MBTA/B&M RAILROAD AND I-95/STATE ROUTE 128 | District 4 | Bridge Preservation | Approved | 2026-07-25 |  | 12344400 | 18601525.5 | 17652550 | Poz Diaz,Genesis
607349 | NORWELL- PEMBROKE- MARSHFIELD- BRIDGE REPLACEMENT, N-24-004=P-05-008, ROUTE 3 (NB & SB) OVER NORTH RIVER | District 5 | Bridge Replacement | 25% Design | 2026-07-11 |  | 79785979.5 | 93008103.03 | 89663080.45 | Kernan,Eamon | AECOM USA, Inc. | 1
613871 | TAUNTON- BRIDGE PRESERVATION, T-01-007, PLAIN STREET BRIDGE OVER THE TAUNTON RIVER | District 5 | Bridge Preservation | Approved | 2026-06-27 |  | 1000000 | 1250000 | 1392031.03 | Napit,Albin | Beta Group, Incorporated
613636 | DIGHTON- BRIDGE REPLACEMENT, D-08-002 (3L9), PLEASANT STREET OVER MUDDY COVE | District 5 | Bridge Replacement | 75% Design | 2026-08-15 |  | 4264079.25 | 3425901.88 |  | Frazier,Greg | Beta Group, Incorporated
613642 | RAYNHAM- TAUNTON- BRIDGE REPLACEMENT, R-02-003=T-01-004 (3M4), SOUTH STREET EAST OVER THE TAUNTON RIVER | District 5 | Bridge Replacement | 25% Design | 2026-08-15 |  | 5081420.25 | 7347388.35 | 6913567.34 | Lamothe,Herrio | Beta Group, Incorporated | 3
608456 | UPTON- CULVERT REPLACEMENT, MILFORD STREET (ROUTE 140) OVER UNNAMED TRIBUTARY TO CENTER BROOK | District 3 | Culvert Replacement | Final Design | 2025-12-27 |  | 2314427.5 | 2903087 | 2634201.5 | Sen,Gautam | BSC Group
611942 | SHEFFIELD- SUPERSTRUCTURE REPLACEMENT, S-10-024, COUNTY ROAD OVER IRONWORKS BROOK | District 1 | Bridge Replacement | Final Design | 2026-02-14 |  | 2194117 | 2785055.21 | 2437528.7 | Chestna,Kristine | BSC Group
612505 | NORTH ADAMS- BRIDGE PRESERVATION, N-14-039, ROUTE 2 OVER SOUTH BRANCH OF THE HOOSIC RIVER AND ROUTE 8 | District 1 | Bridge Preservation | 100% Design | 2026-04-18 |  | 11355050 | 13437357.5 | 13004555 | Breen,Joseph | BSC Group
610544 | PEABODY- MULTI-USE PATH CONSTRUCTION OF INDEPENDENCE GREENWAY AT I-95 AND ROUTE 1 | District 4 | Bike Facility Construction | Final Design | 2026-08-01 |  | 19237029.9 | 23121753.39 | 21368257.89 | Chestna,Kristine | BSC Group
612883 | HARVARD- LANCASTER- BRIDGE REPLACEMENT, H-09-019=L-02-020, JACKSON ROAD OVER NASHUA RIVER | District 3 | Bridge Replacement | 25% Design | 2026-09-30 |  | 13451518 | 19083725.2 | 18432249.3 | Brown,William | BSC Group | 5
610769 | SUTTON- SUPERSTRUCTURE REPLACEMENT, S-33-002, MANCHAUG ROAD OVER MUMFORD RIVER | District 3 | Bridge Replacement | 25% Design | 2026-08-15 |  | 12000019.8 | 17280627.72 | 16444026.73 | Tanoglu,Jacob | C&C Consulting Engineers, LLC | 1
609052 | BROCKTON- INTERSECTION IMPROVEMENTS AT CENTRE STREET (ROUTE 123) AND PLYMOUTH STREET | District 5 | Hwy Reconstr - Restr and Rehab | 75% Design | 2026-06-20 |  | 3211050 | 4886361.25 | 4147936.25 | Dougherty,Kathy | CDM Smith, Inc. | 1
610728 | LEE- RESURFACING AND RELATED WORK ON ROUTE 20 | District 1 | Pavement Rehabilitation | 100% Design | 2026-08-15 |  | 6562456.31 | 7752337.95 | 7356513.52 | Autio,Anni | CDR Maguire, Inc. | 1
611940 | SOMERVILLE- BRIDGE REPLACEMENT, S-17-016 (3GF), WEBSTER AVENUE OVER MBTA & BMRR | District 4 | Bridge Replacement | 75% Design | 2026-08-15 |  | 12120045.2 | 18759474.51 | 16231284.12 | Ramirez,Alwin | CHA Consulting, Inc.
612498 | PITTSFIELD- BRIDGE REPLACEMENT, P-10-003 & P-10-032, SOUTH STREET OVER HOUSATONIC RR & HOUSATONIC RIVER | District 1 | Bridge Replacement | 25% Design | 2026-09-30 |  | 18357560.7 | 26754546.98 | 25158114.45 | Adolphe,Harry | CHA Consulting, Inc. | 2
610657 | EASTHAMPTON- NORTHAMPTON- INSTALLATION OF A SHARED-USE PATH ALONG MOUNT TOM ROAD FROM THE MANHAN TRAIL TO ATWOOD DRIVE | District 2 | Bike Facility Construction | 100% Design | 2026-03-07 |  | 5322808.77 | 6875448.21 | 6207312.77 | Reardon,Muazzez | Chappell Engineering Associates, LLC
612190 | HOLDEN- BRIDGE REPLACEMENT, H-18-004, SALISBURY STREET OVER G&W RAILROAD | District 3 | Bridge Replacement | 75% Design | 2026-05-23 |  | 5985733 | 8150617.08 | 7540122.93 | Soma,Stephen | Chappell Engineering Associates, LLC
607420 | NATICK- SUPERSTRUCTURE REPLACEMENT, N-03-012, BODEN LANE OVER CSX/MBTA | District 3 | Bridge Rehabilitation | 75% Design | 2026-06-27 |  | 13167438 | 17578825.45 | 16525134.68 | Fallon,John | Chappell Engineering Associates, LLC | 3
612176 | HUNTINGTON- BRIDGE REPLACEMENT, H-27-008, ST 112 WORTHINGTON ROAD OVER WATER POND BROOK | District 1 | Bridge Replacement | 25% Design | 2026-09-30 |  | 3040000 | 4896250 | 4231000 | Currier,Thomas | Collins Engineers, Inc. | 1
609440 | ABINGTON- INTERSECTION IMPROVEMENTS AT HANCOCK STREET AND CHESTNUT STREET | District 5 | Traffic Signal Upgrades | Final Design | 2026-01-24 |  | 6318417 | 8551707.46 | 7502909.2 | Freeman,Jonathan | Environmental Partners Group, Inc.
608744 | PROVINCETOWN- CORRIDOR IMPROVEMENTS AND RELATED WORK ON SHANK PAINTER ROAD, FROM ROUTE 6 TO BRADFORD STREET | District 5 | Roadway - Reconstr - Sidewalks and Curbing | 100% Design | 2026-06-20 |  | 13920424 | 16964754.85 | 16014968.65 | Currier,Thomas | Environmental Partners Group, Inc. | 2
607979 | MARION- SHARED USE PATH CONSTRUCTION (PHASE 1), FROM THE MARION-MATTAPOISETT T.L. TO POINT ROAD | District 5 | Bike Facility Construction | 100% Design | 2026-08-15 |  | 5712305.82 | 6690273.44 | 6342042.65 | Yoo,Joseph | Foth | 1
609388 | WENHAM- SAFETY IMPROVEMENTS ON ROUTE 1A | 100% Design | Targeted Modernization - Multiple Locations | 100% Design | 2026-08-15 |  | 4225523 | 6084017.6 | 4936125.3 | Yu,Dongke | Fuss & O'Neill, Incorporated
602843 | GEORGETOWN- RECONSTRUCTION ON ROUTE 97 (W. MAIN STREET) FROM MOULTON STREET TO GROVELAND T.L. | District 4 | Roadway Modernization | 75% Design | 2026-08-22 |  | 8363921 | 11198915.73 | 10758734.48 | Limaye,Janhavi | Fuss & O'Neill, Incorporated
612168 | PITTSFIELD- BRIDGE REPLACEMENT, P-10-040, PONTOOSUC AVE OVER WEST BRANCH HOUSATONIC RIVER RESERVOIR | District 1 | Bridge Replacement | 25% Design | 2026-09-05 |  | 6892411 | 9848718.4 | 9382451.35 | Lamothe,Herrio | Fuss & O'Neill, Incorporated | 3
609068 | SHEFFIELD- BRIDGE REPLACEMENT, S-10-015, KELSEY ROAD OVER SCHENOB BROOK | District 1 | Bridge Replacement | 75% Design | 2026-08-15 |  | 2967747.45 | 4032724.37 | 3668490.63 | Bartus,Joshua | Gannett Fleming Engineers and Architects, P.C. | 1
607677 | LEE- BRIDGE REPLACEMENT, L-05-013, MILL STREET OVER WASHINGTON MOUNTAIN BROOK | District 1 | Bridge Replacement | 25% Design | 2026-09-30 |  | 4403340 | 6850759.6 | 6034301 | Chestna,Kristine | GAROFALO & ASSOCIATES, INC. | 1
612195 | WORCESTER- SUPERSTRUCTURE REPLACEMENT, W-44-091, I-290 OVER EAST CENTRAL STREET | District 3 | Bridge Rehabilitation | 75% Design | 2026-06-20 |  | 27338597.5 | 35738186.81 | 34724831.94 | Tanoglu,Jacob | Gill Engineering Associates, Inc. | 1
605168 | HINGHAM- IMPROVEMENTS ON ROUTE 3A, FROM OTIS STREET/COLE ROAD INCLUDING SUMMER STREET AND ROTARY, ROCKLAND STREET TO GEORGE WASHINGTON BOULEVARD | District 5 | Roadway - Reconstr - Sidewalks and Curbing | 75% Design | 2026-09-30 |  | 21375137 | 31949530.68 | 27188542.83 | Limaye,Janhavi | GM2 Associates, Inc. | 1
608634 | DEERFIELD- BRIDGE REPLACEMENT, D-06-001, UPPER ROAD OVER DEERFIELD RIVER | District 2 | Bridge Replacement | 100% Design | 2026-02-21 |  | 21754266.38 | 25508894.25 | 24368779.02 | Cameron,Christopher | Green International Affiliates, Incorporated
612183 | GREAT BARRINGTON- BRIDGE REPLACEMENT, G-11-002, DIVISION STREET OVER HOUSATONIC RIVER | District 1 | Bridge Replacement | 100% Design | 2026-06-27 |  | 8670082 | 10028124.3 | 9627715.2 | Limaye,Janhavi | Green International Affiliates, Incorporated | 2
612143 | ANDOVER- BRIDGE REPLACEMENT, A-09-015, TEWKSBURY STREET OVER CSX RAILROAD | District 4 | Bridge Replacement | 75% Design | 2026-09-30 |  | 9839389 | 13808275.23 | 12263828.03 | Chestna,Kristine | Greenman-Pedersen, Inc. | 1
610825 | SHREWSBURY- NORTHBOROUGH- REHABILITATION & BOX WIDENING ON ROUTE 20, FROM ROUTE 9 TO SOUTH STREET | District 3 | Hwy Reconstr - Restr and Rehab | 100% Design | 2026-06-27 |  | 35659595.1 | 46356763.87 | 41578013.11 | Reardon,Muazzez | HNTB Corporation | 1
607342 | MILTON- INTERSECTION IMPROVEMENTS AT ROUTE 28 (RANDOLPH AVENUE) & CHICKATAWBUT ROAD | District 6 | Intersection Reconstruction | Final Design | 2025-12-20 |  | 9944768.82 | 11955171.95 | 11390456.7 | Bartus,Joshua | Howard Stein Hudson
612184 | REVERE- BRIDGE REPLACEMENT, R-05-015, REVERE BEACH PARKWAY OVER BROADWAY | District 4 | Bridge Replacement | 100% Design | 2026-06-27 |  | 15427345 | 18462499.75 | 17143128.5 | Chestna,Kristine | Howard Stein Hudson
612002 | LAWRENCE- COMMUNITY DAY ARLINGTON IMPROVEMENTS (SRTS) | District 4 | Roadway Modernization | 100% Design | 2026-07-25 |  | 3341513.77 | 3363018.52 | 3985633.4 | Freeman,Jonathan | Howard Stein Hudson
611974 | MEDFORD- INTERSECTION IMPROVEMENTS AT MAIN STREET/SOUTH STREET, MAIN STREET/MYSTIC VALLEY PARKWAY RAMPS AND MAIN STREET/MYSTIC AVENUE | District 4 | Intersection Reconstruction | 25% Design | 2026-08-29 |  | 7015540.5 | 10303376.7 | 9791209.68 | Frazier,Greg | Howard Stein Hudson
611997 | NEWTON- HORACE MANN ELEMENTARY SCHOOL IMPROVEMENTS (SRTS) | District 6 | Roadway Modernization | Approved | 2026-09-30 |  | 982800 | 1519171 | 1371080 | Freeman,Jonathan | Howard Stein Hudson | 5
605983 | WHATELY- REHABILITATION OF HAYDENVILLE ROAD, FROM CONWAY ROAD TO THE WILLIAMSBURG T.L. (1.7 MILES) | District 2 | Reclamation | 100% Design | 2026-09-30 |  | 10944448 | 13256342.2 | 12428413.8 | Frazier,Greg | Hoyle, Tanner & Associates, Inc.
607231 | WILLIAMSBURG- RECONSTRUCTION OF MOUNTAIN STREET | District 1 | Roadway Modernization | 75% Design | 2026-09-30 |  | 16190808.75 | 14700757.07 | 20570465.72 | Frazier,Greg | Hoyle, Tanner & Associates, Inc. | 2
613295 | GREENFIELD- DECK REPLACEMENT, G-12-022 (144), LOG PLAIN ROAD WEST OVER G&W RAILROAD | District 2 | Bridge Deck Replacement | 100% Design | 2026-01-31 |  | 4894390 | 5997648.5 | 5605429 | Reardon,Muazzez | Jacobs Engineering Group, Inc
609506 | BECKET- LEDGE REMOVAL ALONG ROUTE 8, BETWEEN MM 28.002 AND MM 27.998 | District 1 | Embankment and Ledge Stabilization | 75% Design | 2026-09-05 |  | 4144606 | 5253707.2 | 4706666.6 | Freeman,Jonathan | Jacobs Engineering Group, Inc | 2
613689 | CAMBRIDGE- NEIGHBORHOOD ELECTRIC VEHICLE CHARGING INFRASTRUCTURE (MA287) | District 6 | Roadway - Reconstr - Sidewalks and Curbing | Approved | 2026-08-15 |  | 1041666.67 | 1250000 | 1145833.34 | Lemrise,Koby | Kleinfelder Northeast | 1
611982 | MEDFORD- SHARED USE PATH CONNECTION AT THE ROUTE 28/WELLINGTON UNDERPASS | District 4 | Bike Facility Construction | Final Design | 2026-03-07 |  | 6943138 | 8036373.7 | 7706851.8 | Walsh,Linda | Nitsch Engineering
609204 | BELMONT- COMMUNITY PATH, BELMONT COMPONENT OF THE MCRT (PHASE I) | District 4 | Bike Facility Construction | 75% Design | 2026-08-15 |  | 20340209 | 32556266.48 | 30931756.03 | Currier,Thomas | Nitsch Engineering | 2
610670 | HARWICH- HARWICH ELEMENTARY SCHOOL IMPROVEMENTS (SRTS) | District 5 | Roadway Modernization | Final Design | 2025-12-20 |  | 2605774.5 | 3538232.72 | 2958976.7 | Freeman,Jonathan | Pare Corporation
606352 | WAREHAM- CULVERT AND DAM REPLACEMENT ON CRANBERRY HIGHWAY AT ROUTE 28 AND ROUTE 6, MILL POND DAM OVER AGAWAM RIVER | District 5 | Bridge Replacement | Final Design | 2026-03-28 |  | 25127524.86 | 30050338.62 | 28099848.6 | Adolphe,Harry | Pare Corporation | 2
611953 | SPRINGFIELD- CHICOPEE- GUIDE AND TRAFFIC SIGN REPLACEMENT ON A SECTION OF INTERSTATE 291 | District 2 | Structural Signing | 25% Design | 2026-05-23 |  | 1239115 | 1516198 | 1401026.5 | Timmins,Stephen | Stantec Consulting Services, Inc.
611952 | HARVARD- LITTLETON- ACTON- CONCORD- GUIDE AND TRAFFIC SIGN REPLACEMENT ON A SECTION OF ROUTE 2 | District 3 | Structural Signing | Approved | 2026-06-13 |  | 476000 | 734125 | 735100 | Timmins,Stephen | Stantec Consulting Services, Inc.
613163 | LYNNFIELD- PEABODY- RAIL TRAIL CONSTRUCTION, FROM FORD AVENUE TO NICHOLS LANE (PHASE 1) | District 4 | Bike Facility Construction | Final Design | 2026-07-18 |  | 4873169.5 | 5901323.4 | 5442496.45 | Negah,Shahpar | Stantec Consulting Services, Inc. | 3
610537 | BOSTON- ELLIS ELEMENTARY TRAFFIC CALMING (SRTS) | District 6 | Roadway Modernization | Final Design | 2026-01-17 |  | 1966992.5 | 2448911 | 2312466.75 | Freeman,Jonathan | TEC, Inc.
613903 | LAWRENCE- BRIDGE PRESERVATION, L-04-004 (2PX), UNION STREET OVER NORTH CANAL | District 4 | Bridge Preservation | Approved | 2026-05-02 |  | 1000000 | 1465400 | 1370000 | Poz Diaz,Genesis | TEC, Inc.
612159 | BERNARDSTON- BRIDGE REPLACEMENT, B-10-001, ROUTE 10 OVER FALL RIVER AND DECK REPLACEMENT, B-10-018, ROUTE 10 OVER I-91 | District 2 | Bridge Replacement | 75% Design | 2026-05-23 |  | 28959075 | 38503326.88 | 36580129.38 | Mischel,Gregory | TEC, Inc.
609213 | HARVARD- RESURFACING AND BOX WIDENING ON AYER ROAD, FROM ROUTE 2 TO THE AYER TOWN LINE | District 3 | Resurfacing DOT Owned Non-Interstate | Final Design | 2026-06-27 |  | 9870475 | 14398253.25 | 11561959 | Reardon,Muazzez | TEC, Inc. | 4
613702 | METHUEN- GUIDE AND TRAFFIC SIGN REPLACEMENT ON ROUTE 213 | District 4 | Structural Signing | Final Design | 10/25/2025 (adv). | 965071 | 929846 | 1190663.63 | 1058055.6 | Timmins,Stephen | Tetra Tech, Inc.
613994 | BURLINGTON TO READING- GUIDE AND TRAFFIC SIGN REPLACEMENT ON A SECTION OF I-95/128 | District 4 | Structural Signing | Final Design | 2025-11-15 |  | 1832982.5 | 2236539 | 2064280.75 | Timmins,Stephen | Tetra Tech, Inc.
609409 | SPRINGFIELD- BRIDGE REPLACEMENT, S-24-016, ARMORY STREET OVER CSX MAINLINE & S-24-026, ARMORY STREET OVER ABANDONED CSX | District 2 | Bridge Replacement | Final Design | 2025-12-20 |  | 51083100.7 | 61989362.31 | 57163820.77 | Christakis,Anthony | Tetra Tech, Inc.
610647 | WAREHAM- CORRIDOR IMPROVEMENTS ON ROUTE 6 AT SWIFTS BEACH ROAD | District 5 | Roadway Modernization | Final Design | 2026-03-28 |  | 7672651 | 10498769.15 | 8912428.6 | Dougherty,Kathy | Tetra Tech, Inc. | 4
609277 | NORTH ADAMS- RECONSTRUCTION OF ASHLAND STREET | District 1 | Hwy Reconstr - Restr and Rehab | Final Design | 2026-03-28 |  | 8422625 | 11342811.45 | 9836822.5 | Lamothe,Herrio | Tighe & Bond, Inc.
612895 | FITCHBURG- IMPROVEMENTS AT MEMORIAL MIDDLE SCHOOL (SRTS) | District 3 | Roadway Modernization | 25% Design | 2026-09-30 |  | 1326870 | 2001786.85 | 1811177.56 | Kiel,Adam | Tighe & Bond, Inc. | 2
610535 | WORCESTER- PEDESTRIAN AND BICYCLE IMPROVEMENTS ON PLEASANT STREET | District 3 | Bike Facility Construction | 25% Design | 2026-06-27 |  | 2830418.5 | 4158179.03 | 3966584.68 | Olaoye,Adetoyin | Toole Design Group, LLC
609286 | NORTHAMPTON- DOWNTOWN COMPLETE STREETS CORRIDOR AND INTERSECTION IMPROVEMENTS ON MAIN STREET (ROUTE 9) | District 2 | Roadway Modernization | 75% Design | 2026-08-15 |  | 23206277 | 26314479.38 | 29529089.33 | Shedd,David | Toole Design Group, LLC
606453 | BOSTON- IMPROVEMENTS ON BOYLSTON STREET, FROM INTERSECTION OF BROOKLINE AVENUE & PARK DRIVE TO IPSWICH STREET | District 6 | Roadway Minor Widening | 25% Design | 2026-09-30 |  | 6995766.5 | 8331781.48 | 7798343.15 | Belov,Aleksey | Toole Design Group, LLC | 3
612193 | ANDOVER- BRIDGE PRESERVATION, A-09-022, I-93 OVER MERRIMACK RIVER | District 4 | Bridge Deck Replacement | 75% Design | 2026-08-22 |  | 102375297 | 132000224.55 | 127463219.58 | Belov,Aleksey | Transystems Corporation of Mass. | 1
608862 | SOUTHBRIDGE- BRIDGE REPLACEMENT, S-21-009, MILL STREET OVER MCKINSTRY BROOK & S-21-003, MILL STREET OVER THE QUINEBAUG RIVER | District 3 | Bridge Replacement | Final Design | 2026-03-21 |  | 8935602.5 | 11232072.64 | 9930732.75 | Ramirez,Alwin | Vanasse Hangen Brustlin, Incorporated
608940 | WESTON- INTERSECTION IMPROVEMENTS BOSTON POST ROAD (ROUTE 20) AT WELLESLEY STREET | District 6 | Safety Improvements | Final Design | 2026-03-28 |  | 3225840 | 4139072 | 3706115 | Campbell,Alolade | Vanasse Hangen Brustlin, Incorporated
609061 | CHICOPEE- INTERSECTION IMPROVEMENTS AT MONTGOMERY STREET, GRANBY ROAD, AND MCKINSTRY AVENUE | District 2 | Roadway Modernization | Final Design | 2026-04-18 |  | 11904368.5 | 12829620.64 | 13518280.35 | Freeman,Jonathan | Vanasse Hangen Brustlin, Incorporated
607871 | DARTMOUTH- CORRIDOR IMPROVEMENTS ON ROUTE 6, FROM FAUNCE CORNER ROAD TO HATHAWAY ROAD | District 5 | Hwy Reconstr - Restr and Rehab | 75% Design | 2026-08-15 |  | 10164015.5 | 11024874.44 | 11687022.05 | Currier,Thomas | Vanasse Hangen Brustlin, Incorporated
608961 | WORCESTER- INTERSECTION IMPROVEMENTS ON CHANDLER STREET AND MAY STREET | District 3 | Traffic Signal Upgrades | 75% Design | 2026-08-15 |  | 6109717.5 | 8475277.81 | 7761838.94 | Reardon,Muazzez | Vanasse Hangen Brustlin, Incorporated
608067 | WOBURN- BURLINGTON- INTERSECTION RECONSTRUCTION AT ROUTE 3 (CAMBRIDGE ROAD) & BEDFORD ROAD AND SOUTH BEDFORD STREET | District 4 | Roadway Minor Widening | 75% Design | 2026-09-30 |  | 3445629.75 | 4883749.42 | 4454696.44 | Reardon,Muazzez | Vanasse Hangen Brustlin, Incorporated | 5
612187 | CHICOPEE- BRIDGE REPLACEMENT, C-13-038, I-391 OVER (ST 116) CHICOPEE STREET | District 2 | Bridge Replacement | 25% Design | 2026-04-25 |  | 127402565 | 152022999.75 | 147152871.5 | Belov,Aleksey | WSP USA, Inc. | 1
79 | [5 empty] | 20766716 | 1055998028.19 | 1321492809.31 | 1268320550.48 |  |  | 69
Note: a 9/30 Ad Date means the project will not advertise in the current Ad Year

## FA Summary
SUMMARY
Designer | # of projects
AECOM USA, Inc. | 1
Beta Group, Incorporated | 3
BSC Group | 5
C&C Consulting Engineers, LLC | 1
CDM Smith, Inc. | 1
CDR Maguire, Inc. | 1
CHA Consulting, Inc. | 2
Chappell Engineering Associates, LLC | 3
Collins Engineers, Inc. | 1
Environmental Partners Group, Inc. | 2
Foth | 1
Fuss & O'Neill, Incorporated | 3
Gannett Fleming Engineers and Architects, P.C. | 1
GAROFALO & ASSOCIATES, INC. | 1
Gill Engineering Associates, Inc. | 1
GM2 Associates, Inc. | 1
Green International Affiliates, Incorporated | 2
Greenman-Pedersen, Inc. | 1
HNTB Corporation | 1
Howard Stein Hudson | 5
Hoyle, Tanner & Associates, Inc. | 2
Jacobs Engineering Group, Inc | 2
Kleinfelder Northeast | 1
Nitsch Engineering | 2
Pare Corporation | 2
Stantec Consulting Services, Inc. | 3
TEC, Inc. | 4
Tetra Tech, Inc. | 4
Tighe & Bond, Inc. | 2
Toole Design Group, LLC | 3
Transystems Corporation of Mass. | 1
Vanasse Hangen Brustlin, Incorporated | 6
WSP USA, Inc. | 1
70